## Foglio1
Lead: ISPRA | WP 3 - Schedule |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | GEUS | BGR | TNO | SGU | GeoZS | CGS | BRGM | PGI | NERC | ISPRA | GTK | NGU | RBINS | GSI | LNEG | IGME-ES | GIU | HGI-CGS | ISOR | GBA | SGSS | MBFSZ | LfU | Tot MM
Lead by BGS | Task 3.1 - Standardisation and interoperability analysis |  | M9: D3.1 | [22 empty] | 0 | 25.5
| 3.1.A | User requirments and needs analysis | [18 empty] | 0.5 | 1.5 | 0 | 1 | 1 | 0.5 | 0.5 | 0 | 0.5 | 1 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 9 | bar: M4 to M9
| 3.1.B | Analysis of existing standard to support users | [18 empty] | 0 | 1.5 | 1 | 1 | 1 | 0.5 | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0.5 | 1 | 0 | 16.5 | bar: M7 to M9
Lead by BRGM | Task 3.2 - Data model gap analysis and technical requirements |  | M12: D3.2.1; M15: D3.2.2 | [23 empty] | 21.5
| 3.2.A | Gap analysis and potential extension | [18 empty] | 0 | 1.5 | 0.5 | 1 | 0 | 0.5 | 1.5 | 0 | 0.5 | 1 | 0 | 1 | 0 | 0 | 1.5 | 0 | 0 | 1 | 1.5 | 0 | 1 | 1 | 0 | 13.5 | bar: M9 to M12
| 3.2.B | Technical requirments definition | [18 empty] | 1 | 1.5 | 0 | 1 | 1 | 0.5 | 1 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 8 | bar: M12 to M15
Lead by ISPRA | Task 3.3 - Standards validation procedures |  | M18: D3.3 | [23 empty] | 8.5
| 3.3.A | Abstract Test Suite definition | [18 empty] | 0.5 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 6.5 | bar: M11 to M15
| 3.3.B | Schematron documents and the ETS | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | bar: M15 to M18
|  |  | M1: Total effort for each partner | 2 | 6 | 1.5 | 5 | 3 | 2 | 5 | 1 | 4 | 7 | 0 | 3 | 0 | 0 | 3 | 0 | 1 | 2 | 3 | 2 | 3 | 2 | 0 | 55.5
3.1.A | The sub task works in parallel with T2.2 to transform the extract diverse research products in data model requirments and functionality needs
3.1.B | The sub task starting from the data model requirments has to map these with the existing standard in order to serve datasets in satandard model and to ensure service production, the final result of both the sub task will be D3.1 [M6]
3.2.A | The sub task has to identify the gap of existing standard to map GSP needs/requirments in order to define new extension of these data model or conceptual UML to map the requests. The gap analysis and potential extension will be described in D3.2.1 [M10]
3.2.B | The sub task (should be run in parallel with 3.2.A) has to transform all the data model standard and funcionality needs in technical requirments to pass to WP6 and WP7 in order to implementing data format and encoding in the platform and in the central databases. The TR will be described in D3.2.2 [M12]
3.3.A | The sub task has to write the rules (ATS) to test and validate the datasets conformity to Technical Requirments and Reccomandations; it will run in parallel to 3.3.B in order to produce to validation service prototype tool
3.3.B | The sub task has to transform the ATS in Executeble Test suite or schematron in order to develop the procedure to validate and test the conformity of all the datasets and services produced in GeoERA. These peace of software code will be implemented in WP6 to ensure the usability of Validation service as tool in GIP. The ATS and ETS will be described in D.3.3 [M15].